## Project Details
< Project Name >
Estimates Prepared By
Estimates Reviewed By
Estimates Approved By
References

## Summary (Comparison)
< Project Name > - Activities
# | Activity | Worksheet Number | Effort in Hours
1 | Work Decomposition | 3 | 0
2 | PERT | 4 | 0
3 | Structured Expert Judgment | 5 | 0
4 | Expert Judgment | 6 | 0
AVERAGE TOTAL EFFORT IN PERSON HOURS |  | 0

## Work Decomposition
# | Activity | Effort in hours
<Component #1>
1 | Requirements Analysis
2 | Creation of Test Documentation (Test Plan, Test Cases)
3 | Testing (<Type 1>)
4 | Testing (<Type 2>)
5 | Testing (<Type N>)
6 | Retesting, Confirmation, Regression testing
<Component #2>
1 | Requirements Analysis
2 | Creation of Test Documentation (Test Plan, Test Cases)
3 | Testing (<Type 1>)
4 | Testing (<Type 2>)
5 | Testing (<Type N>)
6 | Retesting, Confirmation, Regression testing
<Component N>
1 | Requirements Analysis
2 | Creation of Test Documentation (Test Plan, Test Cases)
3 | Testing (<Type 1>)
4 | Testing (<Type 2>)
5 | Testing (<Type N>)
6 | Retesting, Confirmation, Regression testing
GRAND TOTAL EFFORT IN PERSON HOURS |  | 0
INSTRUCTIONS: 1. Decompose the work into very small work packages 2. Estimate all small activities 3. Add up separate estimates Each task is broken down into smaller components (up to 2 days!). Then, individual estimates are developed for these tasks. The estimates for the smaller individual components are then aggregated to develop a larger estimate for the entire task.

## PERT
# | Activity | Best case effort in hours | Most likely effort in hours | Worst case effort in hours | Expected case effort in hours
<Component #1>
1 | <Task #1> |  |  |  | 0
2 | <Task #2> |  |  |  | 0
3 | <Task #3> |  |  |  | 0
4 | <Task N> |  |  |  | 0
<Component #2>
1 | <Task #1> |  |  |  | 0
2 | <Task #2> |  |  |  | 0
3 | <Task #3> |  |  |  | 0
4 | <Task N> |  |  |  | 0
<Component #N>
1 | <Task #1> |  |  |  | 0
2 | <Task #2> |  |  |  | 0
3 | <Task #3> |  |  |  | 0
4 | <Task N> |  |  |  | 0
GRAND TOTAL EFFORT IN PERSON HOURS |  | 0
INSTRUCTIONS: When estimating a task, you need to provide three values, as specified above. The three values identified, estimate what happens in an optimal state (best case), what is the most likely, or what we think it would be the worst case scenario. A technique called the Program Evaluation and Review Technique (PERT) allows you to compute an Expected Case that might not be exactly in the middle of the range from best case to worst case (Putnam and Myers 1992, Stutzke 2005). * Optimistic (best case): generally, the shortest time in which the activity can be completed. It is common that there is approximately a 1% chance that the activity will be completed within the optimistic time. (assuming everything proceeds better than is normally expected) * Most likely: time with the highest probability. Note that this time is different from the expected time. (assuming everything proceeds as normal) * Pessimistic time: the longest time that an activity might require. Three standard deviations from the mean is commonly used for the pessimistic time. (assuming everything goes wrong, but excluding major catastrophes)

## Structured Expert Judgment
# | Activity | Best case effort in hours | Most likely effort in hours | Worst case effort in hours | Expected case effort in hours
<Component #1>
1 | Requirements Analysis |  |  |  | 0
2 | Creation of Test Documentation (Test Plan, Test Cases) |  |  |  | 0
3 | Testing (<Type 1>) |  |  |  | 0
4 | Testing (<Type 2>) |  |  |  | 0
5 | Testing (<Type N>) |  |  |  | 0
6 | Retesting, Confirmation, Regression testing |  |  |  | 0
<Component #2>
1 | Requirements Analysis |  |  |  | 0
2 | Creation of Test Documentation (Test Plan, Test Cases) |  |  |  | 0
3 | Testing (<Type 1>) |  |  |  | 0
4 | Testing (<Type 2>) |  |  |  | 0
5 | Testing (<Type N>) |  |  |  | 0
6 | Retesting, Confirmation, Regression testing |  |  |  | 0
<Component #N>
1 | Requirements Analysis |  |  |  | 0
2 | Creation of Test Documentation (Test Plan, Test Cases) |  |  |  | 0
3 | Testing (<Type 1>) |  |  |  | 0
4 | Testing (<Type 2>) |  |  |  | 0
5 | Testing (<Type N>) |  |  |  | 0
6 | Retesting, Confirmation, Regression testing |  |  |  | 0
GRAND TOTAL EFFORT IN PERSON HOURS |  | 0
INSTRUCTIONS: 1. Involve experts 2. Break the big task down 3. Use Range: Worst Case (Pessimistic), Best Case (Optimistic) and Most likely 4. Use Estimation Checklists There are some rules following which Structured Expert Judgment are quite accurate: [1]. People who will actually do the work will create the most accurate estimates. [2]. To improve the accuracy of task-level estimates it is better to separate large tasks into smaller tasks. [3]. Thinking through the worst case result sometimes exposes additional work that must be done even in the best case. But estimated worst cases are often more optimistic than true worst cases. [4]. Creating the Best Case and the Worst Case estimates is just the first step. You're still left with the question of which estimate to use. Optimistic: generally, the shortest time in which the activity can be completed. It is common that there is approximately a 1% chance that the activity will be completed within the optimistic time. (assuming everything proceeds better than is normally expected) Most likely: time with the highest probability. Note that this time is different from the expected time. (assuming everything proceeds as normal) Pessimistic time: the longest time that an activity might require. Three standard deviations from the mean is commonly used for the pessimistic time. (assuming everything goes wrong, but excluding major catastrophes) [5]. Use Estimation Checklists to consider everything you should do. Even experts occasionally forget to consider everything they should do. Simple checklists helps improve accuracy by reminding people of considerations they might otherwise forget. Estimation checklist might contain the following items: Is every estimated item clearly defined? Does the estimate include all the kinds of work needed to complete the task? Does the estimate include all the functionality areas needed to complete the task? Is the estimate broken down into enough detail to expose hidden work? Did you look at documented facts (written notes) from past work rather than estimating purely from memory? Is the estimate approved by the person who will actually do the work? Is the productivity assumed in the estimate similar to what has been achieved on similar assignments? Does the estimate include a Best Case, Worst Case, and Most Likely Case? Is the Worst Case really the worst case? Does it need to be made even worse? Is the Expected Case computed appropriately from the other cases? Have the assumptions in the estimate been documented? Has the situation changed since the estimate was prepared? [6]. Compare actual performance to estimated performance so that you can improve your individual estimates over time. Keep a list of your estimates, and fill in your actual results when you complete them.

## Expert Judgment
# | Activity | Description | Effort in hours
1 | Planning and Control | Test planning includes the following main tasks: 1. Identification of the objectives of testing. 2. Determination of the scope and risks of testing. 3. Identification of the test approach. 4. Implementation the test policy or the test strategy. 5. Determination of the required test resources like people, test environments, VM's, PCs, etc. 6. Scheduling test analysis and design tasks, test implementation, execution and evaluation. 7. Determination of the Exit criteria we need to set criteria such as Coverage criteria. Test control has the following major tasks: 1. Measure and analyze the results of reviews and testing. 2. Monitor and document progress, test coverage and exit criteria. 3. Providing information on testing. 4. Initiative of corrective actions. 5. Making an appropriate decisions.
2 | Analysis and Design | Test analysis and Test Design include the following major tasks: 1. Reviewing of the test basis. 2. Identification of test conditions. 3. Designing the tests. 4. Evaluating of the requirements and system testability. 5. Designing the test environment set-up and identification of required infrastructure and tools.
3 | Implementation and Execution | Test implementation includes the following main tasks: 1. Developing and prioritizing test cases by using techniques and creating test data for them. 2. Creating test suites from the test cases for efficient test execution. 3. Implementing and verifying the test environment. Test execution has the following major task: 1. Execution of test suites and individual test cases following the test strategy. 2. Rerunning of the tests that previously failed in order to confirm a fix (confirmation testing). 3. Logging the outcome of the test execution and recording the identities and versions of the software under tests. 4. Comparing actual results with expected results. 5. Reporting discrepancies as Incidents in case of differences between actual and expected results.
4 | Evaluating exit criteria and Reporting | Exit criteria come into picture, when: — Maximum test cases are executed with certain pass percentage. — Bug rate falls below certain level. — When achieved the deadlines. Evaluating exit criteria includes the following major tasks: 1. Checking the test logs against the exit criteria specified in test planning. 2. Assessing if more test are needed or if the exit criteria specified should be changed. 3. Writing a test summary report for stakeholders.
5 | Test Closure activities | Test closure activities include the following main tasks: 1. Checking which planned deliverables are actually delivered and ensuring that all incident reports have been resolved. 2. Finalizing and archiving testware such as scripts, test environments, etc. for later reuse. 3. Handover of the testware to the maintenance organization. They will give support to the software. 4. Evaluating how the testing went and learning lessons for future releases and projects.
GRAND TOTAL EFFORT IN PERSON HOURS |  |  | 0
INSTRUCTIONS: 1. Involve expert 2. Estimate tasks according to Foundation Test Process or own test strategy Expert Judgment technique is the least accurate method of estimation.

## Helpful Questions
Questions to align Quality expectations at the beginning of project:
Purpose: | * Set a list of quality expectations and prioritize them (there is no chance to satisfy all the expectations at once) * Define the quality goal based on the expectations * Take into consideration quality goals while defining metrics that will help to track the progress toward the goals * Take quality goals into consideration while defining/adjusting testing process.
Questions to start with | 1. What does “qualitative software” mean to client (qualitative enough to be released)? 2. What does the “qualitative testing” mean to client (quality of a service in case client treat testing as a service)?
The questions to “help” client define the quality expectations | * Should software be well-looking, to be qualitative? * Should software be fast, to be qualitative? How fast? (in seconds) Is that applicable to every feature in the product or some might not correspond to that exact performance? * Should software be easily maintainable? What does “maintainable” mean for you? (time to change code, the confidence in changes done, time to deliver and deploy hot-fix, time need to introduce new developer into dev process, etc.) * Can software have defects and be qualitative at the same time? * Which defects would be acceptable for you? * How many defects in software is acceptable? * Would the other deliverables except working build influence your perception of quality? E.g. Test summary report, Known issues list, User Guide, etc. * Would software, delivered on time, but with limited functionality qualitative to you? * Would software, delivered later than planned, but in planned scope and without any defects, qualitative to you? * Could something influence your perception of QA team performance except deliverables they produce? E.g. could the time required to get a response from QA team on some your questions influence on your perception of quality of our work? * Etc.
Processes and general questions | * What tools client has for Project Management and Test Management? * What would be tested (scope)? * Is there any testing team that works for customer? If yes, what is the structure? How we will cooperate? * How will look test reporting? * What documents BA and PO will create that we can use for testing, for example: Business flows, data flows, User Stories, etc. * Which test and project metrics will be needed? * Propose some metrics (create minimum plan): * Number of open defects * Number of defects found * Story Points closed in sprint * etc.? * Is there any test process set with the customer? If yes check if not set: * Defect management * Test reporting * UAT * ... * Who will create user manual? * Propose, design survey for end users about new product after implementation
Types of tests needed | Manual tests that can be provided: * Documentation Testing * Smoke test * Sanity test * Concurrency testing * Cross browser testing * Accessibility * User Acceptance testing * Tests on devices that software was designed for * Web-services testing * User experience & Usability testing * Security smoke tests * Testing forms * Logs testing * Reports testing * Disaster recovery tests * System Availability testing
What types of tests client would like to have additionally? | * Automation tests? * Security tests? * Performance tests? * Accessibility tests? * User experience tests?
Automation | * If automation or performance needed - (create questions) * Which programing language is used for development? * Is there any automation set within client infrastructure? * Is there CI/CD set? * …
Security testing | * Should we test against OWASP? * Is there external company certification needed? * Who will decide which vulnerabilities should be resolve? * …
Performance testing | * If Performance tests needed - what are requirements? * What is the type of application and its architecture? * What are the known current as well as previous performance bottlenecks? * Which application scenarios to be tested? * What will be the workload model? * What are the performance goals? * What is the application type? * In which technology/platform the application is developed? * Which database is used? * Which Application server is running with the system? * How is the targeted application look like? (Please specify all servers and network appliances configurations and their interaction mechanism) * What is the protocol between the client and server? * Is the client browser version dependent in case of web application? * Will separate test environment be provided to do a performance test run? * Any preference on performance tools? * What is the current project lead time for testing activities? * If selected scenarios require some unique inputs then these should be specified. * Do you have statistics, how many users visit the application in 24 hours? * What is the peak load time on production server? * How many users access the application in peak load time? * What is the average user session time on application? * What will be user distribution on test scenarios? * How many users are intended to access application simultaneously? * Are there any time constraints for running the test? * Is it required to generate load from multiple geographical regions? If yes, which? * Have you set any acceptable maximum transaction completion time? * Have you set the expected throughput of the application? * Which is the most important performance goal of the application? * What will the acceptance criteria for each performance test?
Accessibility testing | * What types of disability we need to take under consideration? * What tools should we use? Only extensions to the web-browser or desktop as well?
User experience tests | * Describe end users * Should User experience tests should be provided by software testers or we will use end users and organize sessions?
Configuration questions | * How infrastructure for test servers will look like? Who will be the owner? What is Production configuration? Who will take care of staging and testing environments? * Ask for requirements: * screen resolutions, * Supported web-browsers and devices * NFR (non functional requirements)